## Sheet1
Activity | Process Schedule
| APRIL |  |  |  | MAY |  |  |  | JUNE
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
E-R Diagram | MAY Week 1: Checkpoint 1 (3 May 2021)
Database | MAY Week 4: Checkpoint 2 (24 May 2021)
Relational Design | MAY Week 4: Checkpoint 2 (24 May 2021)
User Interfaces | MAY Week 4: Checkpoint 2 (24 May 2021)
Development Schedule | MAY Week 4: Checkpoint 2 (24 May 2021)
Coding | JUNE Week 3: Checkpoint 3 (14 June 2021)
Testing | JUNE Week 4: Final Project (21 - 25 June 2021)
dalam proses pengerjaan
Checkpoint yang sudah dilewati
Checkpoint yang belum dilewati